{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["社会投资类","投资类（小型项目） ","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"社会投资类","index":0,"n_rows":32,"n_cols":13,"rows_kept":32,"merged":[[0,0,0,12],[1,1,1,2],[1,5,1,6],[1,8,1,10],[1,11,1,12],[2,0,11,0],[2,1,2,2],[2,5,2,6],[2,8,2,9],[4,8,5,9],[4,11,5,12],[5,5,5,6],[6,1,6,2],[8,5,8,6],[8,8,8,9],[8,11,8,12],[9,8,9,9],[10,5,10,6],[12,0,32,0],[13,1,14,2],[13,5,14,6],[13,8,13,9],[13,11,13,12],[15,8,15,9],[16,5,16,6],[18,1,18,6],[19,1,19,2],[19,5,19,6],[19,8,19,9],[21,1,21,2],[21,5,21,6],[21,8,21,9],[22,8,22,9],[23,1,23,2],[23,5,23,6],[25,5,25,9],[26,5,27,6],[26,8,27,9],[29,1,29,12],[30,1,30,2],[30,5,30,6],[30,8,30,9]],"flags":["formulas_cached_only"]}
["社会投资类项目审批流程图（42个工作日）"]
[null,"立项用地规划许可阶段\n（发改委牵头-6个工作日）",{"$nulls":3},"工程建设许可阶段\n（自然资源和规划局牵头-20个工作日）",null,null,"施工许可阶段\n（行政审批局牵头-7个工作日）",null,null,"竣工验收阶段\n（住建局牵头-9个工作日）"]
["审批主流程","建设项目用地预审与选址意见书",{"$nulls":3},"项目规划总平面图",null,null,"建设工程消防设计审查"]
[null,"自然资源和规划局",3,null,null,"自然资源和规划局",7,null,"住建局",4]
[{"$nulls":8},"应建防空地下室的新建民用建设项目防空地下室防护设计（施工）审查\n",null,null,"联合验收（规划、土地、消防、人防、档案等）"]
[{"$nulls":5},"建筑设计方案审定"]
[null,"企业投资项目核准",{"$nulls":3},"自然资源和规划局",7,null,"行政审批局",4,null,"住建局",6]
[null,"行政审批局",3]
[{"$nulls":5},"建设工程（含临时建设）规划许可证核发",{"$nulls":5},"竣工验收备案"]
[null,"企业投资项目备案",{"$nulls":3},"自然资源和规划局",6,null,"建筑工程施工许可证核发",null,null,"住建局",3]
[null,"发改局","即办",null,null,"供排水接入",null,null,"行政审批局",3]
[{"$nulls":5},"行政审批局",5]
["并行审批主流程"]
[null,"建设项目压覆重要矿产资源审查",{"$nulls":3},"在风景名胜区内从事建设、设置广告、举办大型游乐活动以及其他影响生态和景观活动许可",null,null,"占用、挖掘城市道路审批",null,null,"不动产登记"]
[{"$nulls":8},"行政审批局",5,null,"不动产登记中心",1]
[null,"自然资源和规划局",6,null,null,"行政审批局",6,null,"施工图设计文件审查情况备案（联合图审、含消防、技防、人防）"]
[{"$nulls":5},"江河、湖泊新建、改建或扩大排污口审核",null,null,"住建局",4]
[{"$nulls":5},"行政审批局",8]
[null,"第一、第二阶段可并联或并行办理事项"]
[null,"拆除人民防空工程审批",{"$nulls":3},"占用农业灌溉水源、灌排工程设施审批",null,null,"因工程建设需要拆除、改动、迁移供水、排水与污水处理设施审核"]
[null,"住建局",4,null,null,"行政审批局",8,null,"行政审批局",7]
[null,"在宗教活动场所内改建或新建建筑物审批",{"$nulls":3},"在文物保护单位的保护范围内进行其他建设工程或者爆破、钻探、挖掘等作业审批"]
[null,"行政审批局",3,null,null,"行政审批局",10,null,"工程建设涉及城市绿地、数目审批"]
[null,"建设用地（含临时用地）规划许可证核发",{"$nulls":3},"涉及国家安全事项的建设项目审批",null,null,"行政审批局",6]
[null,"自然资源和规划局",3,null,null,"公安局",6]
[{"$nulls":5},"第二、第三阶段可并联或并行办理事项"]
[{"$nulls":5},"应建防空地下室的新建民用建设项目防空地下室防护设计（规划）审查\n",null,null,"市政公用设施报装"]
[]
[{"$nulls":5},"行政审批局",7,null,"自来水厂、供电局、中茂燃气",10]
[null,"第一、第二、第三阶段可并联或并行办理事项"]
[null,"建设项目环境影响评价审批",{"$nulls":3},"生产建设项目水土保持方案审批",null,null,"节能审查",null,null,"取水许可审批"]
[null,"行政审批局",7,null,null,"行政审批局",10,null,"行政审批局",5,null,"行政审批局",12]

{"sheet":"投资类（小型项目） ","index":1,"n_rows":17,"n_cols":13,"rows_kept":17,"merged":[[0,0,0,12],[1,1,1,2],[1,5,1,6],[1,8,1,10],[1,11,1,12],[2,0,3,0],[2,5,2,6],[2,8,2,9],[2,11,2,12],[5,0,15,0],[5,8,5,10],[6,8,6,9],[8,4,8,8],[9,5,9,7],[10,5,10,6],[13,1,13,2],[13,5,13,6],[13,8,13,9],[16,0,16,12]],"flags":["formulas_cached_only"]}
["社会投资建设低风险产业类备案项目（小型项目）审批流程图（14个工作日）"]
[null,"立项用地规划许可阶段\n（发改委牵头-0个工作日）",{"$nulls":3},"工程建设许可阶段\n（自然资源和规划局牵头-7个工作日）",null,null,"施工许可阶段\n（行政审批局牵头-3个工作日）",null,null,"竣工验收阶段\n（住建局牵头-4个工作日）"]
["审批主流程","企业投资项目备案",{"$nulls":3},"建设工程（含临时建设）规划许可证核发",null,null,"建筑工程施工许可证核发（质量监督手续）",null,null,"联合验收（含不动产登记）"]
[null,"发改局","即办",null,null,"自然资源和规划局",6,null,"行政审批局",3,null,"住建局",4]
[]
["并行审批主流程",{"$nulls":7},"施工图设计文件审查情况备案（联合图审、含消防、技防、人防）"]
[{"$nulls":8},"住建局",null,3]
[]
[{"$nulls":4},"第二、第三阶段可并联或并行办理事项"]
[{"$nulls":5},"市政公用设施报装"]
[{"$nulls":5},"自来水厂、供电局、中茂燃气",null,8]
[]
[{"$nulls":5},"第一、第二、第三阶段可并联或并行办理事项"]
[null,"建设项目环境影响审批",{"$nulls":3},"建设用地（含临时用地）规划许可证核发",null,null,"节能审查"]
[null,"行政审批局",7,null,null,"自然资源和规划局",6,null,"行政审批局",5]
[]
["注：该流程图仅限于已获得项目建设用地审批手续和已完成区域评估的工业园区、经济技术开发区等各类产业园区内生产工艺简单的项目（如标准厂房、普通仓库等）和小型项目，以及园区外总面积不大于10000平当米，高度不超过24米，功能单一，技术要求简单的新建、改建、扩建的社会投资备案类低风险项目（设计易燃易爆、有毒有害等安全保护项目、设计生态环境影响大的项目除外）。"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}